## Tasks
Task ID | Task Group | Depeneddncy ID | Requirement ID | Description | Reponsible | Accountable | Informed | Consulted | Due Date | Current Status | Ststus Update
T-00001 |  |  | Q-0012 | Enhance the Existing ZMM_PURCO | Eslam Soliman | Riyad Alqadhi |  | Kareem Eid | 15.01.2025 | Handover the Task
T-00002 |  | D-0001 |  | Activate SLA on Romansiah it Support Portal | Kareem Eid | Abduljalil | Arete | -

## Dependency
Dependency ID | Dep Group | Task ID | Requirement ID | Description | Reponsible | Accountable | Informed | Consulted | Due Date | Current Status | Ststus Update
D-0001 |  |  |  | Sign the AMS Contract | CEO | CTO | PMO

## Assumptions
Assumption Id

## Issue
Issue ID | Issue Group | Task Group | Requirement ID | Type | Class | Owner | Status | Description | Source Type | Ref Source | Created At | Priority | Deliverables 1 | D1 Status | Deliverables 2 | D2 Status | Last Update | Update Date
I-0001 |  |  |  | Inquiry | HXM | Ahmed Al-Kalaly | Open | Leave Provesioning at ID:14872 | Ticket | 3584 | 08.01.2026 | High
I-0002 | IG-A001 |  |  | Inconvienice | FICO | Rashad Abduljalil | Open | Error at Report Asset Balance | Ticket | 3567 | 07.01.2026 | Very High |  |  |  |  | Waiting for Arete Basis Team | 08.01.2026
I-0003 | IG-A001 |  |  | Inconvienice | FICO | Muhammed Mahdy | Open | Error at trial Balance Report | Ticket | 3573 | 07.01.2026 | Very High |  |  |  |  | Waiting for Arete Basis Team | 08.01.2026
I-0004 |  |  |  | Inconvienice | HXM | Ahmed Al-Kalaly | Open | Workflow is not initiating for many Employees | Ticket | 3583 - 3416 | 07.01.2026 | Very High
I-0005 |  |  |  | Inconvienice | FICO | Asseel Ma'tary | Open | Clearing for Application Sales Accounts | Ticket | 3259 | 27.10.2025 | High |  |  |  |  | Can't Be Done for all Transactions, must be solved | 04.12.2025
I-0006 |  |  |  | Error | FICO | Abdullah Al-Ghilli | Open | Profit Segment Requirement at Payroll Clearing | Ticket | 3569 | 01.01.2026 | Very High |  |  |  |  | under Invistigation by Abdallah Hammed | 08.01.2026
I-0007 |  |  |  | Inconvienice | HXM | Ahmed Al-Kalaly | Open | Secondment | Ticket | 3530 | 21.12.2025 | High |  |  |  |  | Waiting for Arete to Invistigate Solution | 08.01.2026
I-0008 |  |  |  | Inconvienice | FICO | Muhammed Noah | Open | Department Discounts - to be Automatically Transffered to the Expenses | Ticket | 3552 | 28.12.2025 | Very High |  |  |  |  | Waiting for Arete to Invistigate Solution | 08.01.2026
I-0009 |  |  |  | Error | PM | Kareem Eid | Open | Excel cannot be Exported at IW38 / IE05 Fiori | Ticket | 3247 | 26.10.2025 | Very High
I-0010 |  |  | Q-0028 | Inconvienice | HXM | Ahmed Al-Kalaly | Open | secondement is not fitting to Romansiah Business | Ticket | 3416 | 01.12.2025 | High |  |  |  |  | Waiting for Arete to Invistigate Solution | 08.01.2026

## Requirements
ID-Code | Task Group | Issue Group | created at | Type | Class | Category | Aggrement | Owner | Description | Source Type | Ref Source | Status | Priority | Deliverables 1 | D1 Status | Deliverables 2 | D2 Status | Last Update | Update Date
Q-0041 |  |  | 09.01.2026 | WRICEF | Report | CAR |  | Rashad Abduljalil | Report for Consignments to Customers | Ticket | 3594 | Open | Very High | FSD |  | TSD |  | Ticket Opened | 09.01.2026
Q-0042 |  |  | 09.01.2026 | WRICEF | Report | CAR |  | Rashad Abduljalil | Report for Loyality points and Wallet | Ticket | 3593 | Open | Very High | FSD |  | TSD |  | Ticket Opened | 09.01.2026
Q-0001 |  |  | 22.10.2025 | WRICEF | Report | FICO |  | Abdullah Al-Ghilli | Bank Statements Reports | Ticket | 3192 | Open | High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0002 |  |  | 22.10.2025 | WRICEF | Report | FICO |  | Abdullah Al-Ghilli | Cash Flow Report | Ticket | 3193 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0003 |  |  | 22.10.2025 | WRICEF | Report | FICO |  | Rashad Abduljalil | VAT Report | Ticket | 3199 - 3366 | Pending | Medium | FSD |  | TSD |  | Waitingfor Confirmation from BPO | 11.01.2026
Q-0005 |  |  | 22.10.2025 | Solution | Form | FICO |  | Rashad Abduljalil | Print GL statements - customer Statement - Vendor Statement | Ticket | 3198 | Closed | Very High | FSD |  |  |  | Delivered T Codes ZFI_CAS / ZGL_State ZSTATEMENT_OF_ACCT | 23.12.2025
Q-0009 |  |  | 26.10.2025 | WRICEF | Report | FICO |  | Muhammed Mahdy | Scrap Cost as Materials Only | Ticket | 3237 | Closed | Very High | FSD |  | TSD |  | Delivered T Codes ZCOSD / ZCOSD2 | 19.11.2025
Q-0010 |  |  | 26.10.2025 | WRICEF | Report | FICO |  | Riyadh Qadhi | Report of Meals Profitability | Ticket | 3238 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0011 |  |  | 26.10.2025 | WRICEF | Report | FICO |  | Riyadh Qadhi | Report of Branch Profitability | Ticket | 3238 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0014 |  |  | 26.10.2025 | WRICEF | Report | FICO |  | Muhammed Mahdy | Income Statement | Ticket | 3241 | Open | Very High | FSD |  | TSD |  | Waiting for Arete Clarification | 24.12.2025
Q-0015 |  |  | 26.10.2025 | WRICEF | Report | FICO |  | Alakhshar | Forms Printout for Finance | Ticket | 3242 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0018 |  |  | 12.11.2025 | WRICEF | Customization | FICO |  | Abdullah Al-Ghilli | Upload Supplier InvoiceCustomized Program | Ticket | 3351 | Pending | Very High | FSD |  | TSD |  | Waiting Alakhshar Approval | 28.12.2025
Q-0019 |  |  | 16.11.2025 | WRICEF | Form | FICO |  | Asseel Ma'tary | Print Finance Invoice | Ticket | 3354 - 3361 | Solved | Medium | FSD |  | TSD |  | ZINVOICE_PRINT | 21.12.2025
Q-0020 |  |  | 05.11.2025 | WRICEF | Report | FICO |  | Riyadh Qadhi | Cost Formula Report | Ticket | 3333 | Open | High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0022 |  |  | 16.11.2025 | WRICEF | Customization | FICO |  | Abdullah Al-Ghilli | Automatic Profit Center at Post Cash Journal Entries | Ticket | 3355 | Pending | Very High | FSD |  | TSD |  | Waiting Alakhshar Approval | 28.12.2025
Q-0023 |  |  | 16.11.2025 | WRICEF | Customization | FICO |  | Abdullah Al-Ghilli | Cumulative Balance for Bank Statement | Ticket | 3358 | Pending | Very High | FSD |  | TSD |  | Waiting Alakhshar Approval | 28.12.2025
Q-0043 |  |  | 09.01.2026 | WRICEF | Report | FICO |  | Rashad Abduljalil | Report of Fixed Assets | Ticket | 3592 | Open | Medium | FSD |  | TSD |  | Ticket Opened | 09.01.2026
Q-0046 |  |  | 19.11.2025 | Configuration | Field Selection | FICO |  | Rashad Abduljalil | Attachment Enablement at Invoicing | Ticket | 3382 | Pending | Very High | Configuration Guide |  | - |  | Waiting for Rashad reponse | 22.11.2025
Q-0053 |  |  | 05.01.2026 | Solution | Cycle | FICO |  | Muhammed Noah | Change the Financial Assesments for Revenues Distributions of Liver Goods | Ticket | 3577 | Open | High | FSD |  | TSD |  | Waiting for FICO Consultant invistigation | 11.01.2026
Q-0054 |  |  | 03.11.2025 | WRICEF | Enhancement | FICO |  | Abdullah Al-Ghilli | American Express | Ticket | 3327 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0055 |  |  | 09.12.2025 | WRICEF | Report | FICO |  | Abdullah Al-Ghilli | Create Report to Get Vat or Commissions per House bank or bank account number | Ticket | 3482 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0056 |  |  | 01.07.2025 | WRICEF | Interface | FICO | CR - | Rashad Abduljalil | IFRS 16 Integration | RFC |  | Closed | Very High | FSD |  | TSD |  | Delivered and Tested | 30.12.2025
Q-0028 |  |  | 01.12.2025 | Configuration | Cycle | HXM |  | Ahmed Al-Kalaly | secondement is not fitting to Romansiah Business | Ticket | 3414 | Pending | High | FSD |  |  |  | Waiting for Arete Invistigation to change the Solution | 08.01.2026
Q-0029 |  |  | 02.12.2025 | WRICEF | Form | HXM |  | Ahmed Al-Kalaly | Pay Slip Form | Ticket | 3417 | Pending | High
Q-0030 |  |  | 02.12.2025 | WRICEF | Form | HXM |  | Ahmed Al-Kalaly | Vacation Form | Ticket | 3417 | Pending | High
Q-0031 |  |  | 02.12.2025 | WRICEF | Form | HXM |  | Ahmed Al-Kalaly | EOS Form | Ticket | 3417 | Pending | High
Q-0032 |  |  | 02.12.2025 | WRICEF | Form | HXM |  | Ahmed Al-Kalaly | Secondement Form | Ticket | 3417 | Pending | High
Q-0033 |  |  | 02.12.2025 | WRICEF | Form | HXM |  | Ahmed Al-Kalaly | Loan Form | Ticket | 3417 | Pending | High
Q-0039 |  |  | 04.01.2026 | WRICEF | Report | HXM |  | Ahmed Al-Kalaly | Reports for Compensations | Ticket | 3574 | Pending | Very High | FSD |  | TSD |  | Waiting For Kalaly Reposnd | 10.01.2026
Q-0045 |  |  | 08.01.2026 | WRICEF | Report | HXM |  | Rashad Abduljalil | Report for Employee Benefits | Ticket | 3585 | Open | Very High | FSD |  | TSD |  | Ticket Opened | 08.01.2026
Q-0048 |  |  | 29.12.2025 | Authorization | Authorization | HXM |  | Alakhshar | Authorization for 476 & 6252 for ECP | Ticket | 3561 | Open | Very High | - |  |  |  | Approved by HR Director | 30.12.2025
Q-0049 |  |  | 04.12.2025 | WRICEF | Report | HXM |  | Salman Al-ghithi | Report for Employees Data | Ticket | 3443 | In-Process | High | Access Manual
Q-0050 |  |  | 21.12.2025 | Configuration | Payment Components | HXM |  | Ahmed Al-Kalaly | Payment Component for Travel Tickets | Ticket | 3529 | Open | High | Configuration Guide |  |  |  | Meeting will Conducted at 11.01.2026 Based on this Meeting at 08.01.2026 | 08.01.2026
Q-0051 |  |  | 04.12.2025 | WRICEF | Report | HXM |  | Salman Al-ghithi | Report for Components of Tickets, Permits and Iqama And Medicals | Ticket | 3453 | Open | High | Access Manual |  |  |  | Meeting to be conducted for Explore the Requirement | 07.01.2026
Q-0012 |  |  | 26.10.2025 | WRICEF | Report | MM |  | Riyadh Qadhi | Purchasing Comparison between two periods | Ticket | 3239 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0013 |  |  | 26.10.2025 | WRICEF | Report | MM |  | Riyadh Qadhi | Material Diversion | Ticket | 3240 | Open | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0016 |  |  | 02.11.2025 | WRICEF | Workflow | MM |  | Muhammed Lotfy | Activate Email on Workflows | Ticket | 3320 | Open | Medium | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0017 |  |  | 02.11.2025 | Configuration | Master Data | MM |  | Mosleh Qahtan | Create Storage Locations Per Department | Ticket | 3322 | Open | Medium | Configuration Guide |  |  |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0027 |  |  | 27.11.2025 | WRICEF | Report | MM |  | Riyadh Qadhi | In/Out Materials report | Ticket | 3404 | Pending | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0034 |  |  | 01.04.2024 | WRICEF | Enhancement | MM |  | Muhammed Mahdy | Check on User Assignment to Cost Center at Migo | Explore | - | Closed | Medium | FSD |  | TSD |  | Deliverd at Pre-Live Phase | 01.04.2025
Q-0035 |  |  | 06.11.2025 | WRICEF | Report | MM |  | Ibrahim Saeed | Create Report to Get Procurement Details of Materials | Ticket | 3341 | Open | Low | FSD |  | TSD |  | Ticket Opened | 06.11.2025
Q-0036 |  |  | 06.11.2025 | WRICEF | Report | MM |  | Ibrahim Saeed | Create Report Display scrapped Value | Ticket | 3544 | Open | Low | FSD |  | TSD |  | Ticket Opened | 06.11.2025
Q-0037 |  |  | 06.11.2025 | WRICEF | Report | MM |  | Ibrahim Saeed | Create Report link PO to Pr with Finance Details | Ticket | 3543 | Open | Low | FSD |  | TSD |  | Ticket Opened | 06.11.2025
Q-0038 |  |  | 06.11.2025 | WRICEF | Report | MM |  | Ibrahim Saeed | Create Report of what Withdrawed from plant to plant | Ticket | 3458 | Open | Low | FSD |  | TSD |  | Ticket Opened | 06.11.2025
Q-0044 |  |  | 08.01.2026 | Configuration | Field Selection | MM |  | Alakhshar | Dimm Posting Date at Migo | Ticket | 3591 | Open | Medium | Configuration Guide |  | - |  | Ticket Opened | 08.01.2026
Q-0021 |  |  | 05.11.2025 | WRICEF | Report | PM | Internal | Al-Abdally | Transferred Assets Report | Ticket | 3337 | Closed | High | FSD |  | TSD |  | ZAST_REP | 06.01.2026
Q-0024 |  |  | 19.11.2025 | WRICEF | Customization | PM |  | Al-Abdally | change logic of Approvals for departments to be with Functions Locations | Ticket | 3377 | Pending | Medium | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0047 |  |  | 11.01.2026 | Authorization | Authorization | PMO |  | Kareem Eid | Create Authorization Matrix Template | PMO | - | Open | Very High | Template
Q-0004 |  |  | 23.10.2025 | Configuration | Workflow | PS |  | Rashad Abduljalil | Project Creation Workflow | Ticket | 3207 | Pending | High | Configuration Guide |  |  |  | Waiting for Rashad response | 27.10.2025
Q-0052 |  |  | 01.07.2025 | WRICEF | Form | PS |  | Ziyad Makhlafy | SES Form for Projects new Version | Ticket | 3421 | Open | High | FSD |  | TSD |  | Waiting for Wricef Status | 11.01.2026
Q-0006 |  |  | 26.10.2025 | WRICEF | Report | SD |  | Rashad Abduljalil | Consignment Report | Ticket | 3222 | Open | Medium | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0007 |  |  | 26.10.2025 | WRICEF | Report | SD |  | Asseel Ma'tary | Sales Report | Ticket | 3223 | Open | Medium | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0008 |  |  | 26.10.2025 | WRICEF | Report | SD |  | Asseel Ma'tary | Invoice Report | Ticket | 3225 | Open | Medium | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0025 |  |  | 25.11.2025 | WRICEF | Report | SD |  | Asseel Ma'tary | Report of Customers | Ticket | 3399 | Pending | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution | 11.01.2026
Q-0026 |  |  | 26.11.2025 | WRICEF | Report | SD |  | Asseel Ma'tary | Report of sales Aggregators Rebates | Ticket | 3402 | Pending | Very High | FSD |  | TSD |  | Waiting for PMO Wricef Distribution / plus invistigate if any duplication of requirement | 11.01.2026
Q-0040 |  |  | 09.01.2026 | WRICEF | Report | SD |  | Rashad Abduljalil | Report of Downpayments and Reservations | Ticket | 3595 | Open | Very High | FSD |  | TSD |  | Ticket Opened | 09.01.2026